## Slide 1: CS 501: Software Engineering Fall 2000
Lecture 4
Management I: Project Management

## Slide 2: Administration
• Assignment 1 has been posted to the web site. Note that submission is by email to the senior Teaching Assistant.
• Remember to copy email about the course to the Teaching Assistants.
• Readings about Requirements Analysis and Definition have been posted to the web site.

## Slide 3: OS 360
The operating system for the IBM 360 was two years late.
Question: How does a project get two years behind schedule?
Answer: One day at a time!
Fred Brooks Jr.,The Mythical Man Month

## Slide 4: The Aim of Project Management
To complete a project:
• On time
• On budget
• With required functionality
• To the satisfaction of the client
• Without exhausting the team

## Slide 5: The Project Manager
• Create and maintain the schedule
• Should track progress against schedule
• Keep some slack in the schedule
• Be continually making adjustments:
Start activities before previous activity complete
Sub-contract activities
Renegotiate deliverables
• Keep senior management informed

## Slide 6: Project Planning Methods
The Critical Path Method, Gantt charts, Activity bar charts, etc. are roughly equivalent.
These methods are best when:
• Model is updated regularly (e.g., monthly)
• The structure of the project is well understood
• The time estimates are reliable
• Activities do not share resources
[Critical Path Method is excellent for large construction projects.]

## Slide 7: Example: An Open University Course
Deliverables:
16 Written texts (bound in pairs)
8 Television programs
8 Radio programs
4 Computer programs
1 Home experimental kit (scientific calculator)
4 Assignments and sample solutions

## Slide 8: Flexibility
Schedule: Dates for broadcasting TV and radio programs are fixed. Printing and mailings can be accelerated if overtime is used.
Functionality: The course team can decide what goes into the components of the course.
Resources: The size of the course team can be increased slightly.

## Slide 9: Scheduling: Critical Path Method
An activity
A dummy activity
An event
A milestone

## Slide 10: Critical Path Method
Edit
Unit 3
Print
Unit 3
Revise
Unit 3
Mail
Unit 3
other
activities
START
END

## Slide 11: Critical Path Method
Edit
Unit 3
Typeset
Unit 3
Revise
Unit 3
Mail
Units 3/4
other
activities
Edit
Unit 4
Print
Units 3/4
Revise
Unit 4
other
activities
Typeset
Unit 4
START

## Slide 12: Critical Path Method
START
Edit
Unit 3
Script
TV 2
Make
TV 2
Edit
Unit 4
Prototype Computer 1
Program
Computer 1
Document
Computer 1
Mail
Delivery

## Slide 13: Time Estimates for Activities (Weeks)
6
4
2
2
3
3
1
3
3
8
2
1
1
4
12
12
1
4

## Slide 14: Earliest Start Dates
6
4
2
2
3
3
1
3
3
8
2
1
1
4
12
12
1
4
0
1
12
12
4
15
17
17
17
19
22
26
23
25

## Slide 15: Latest Start Dates
6
4
2
2
3
3
1
3
3
8
2
1
1
4
12
12
1
0
11
12
14
13
15
17
17
17
20
23
26
24
25
4

## Slide 16: Critical Path
0/0
1/11
12/12
12/14
4/13
15/15
17/17
17/17
17/17
19/20
22/23
26/26
23/24
25/25

## Slide 17: Slack
0/0
1/11
17/17
23/24
10
5
0
12/12
12/14
4/13
15/15
17/17
17/17
19/20
22/23
26/26
25/25
10
0
0
0
0
0
0
2
2
9
9
1
1
3
1
1

## Slide 18: Key Personnel
In computing, not all people are equal:
• The best are at least 5 times more productive
• Some tasks are too difficult for everybody
Adding more people adds communications complexity
• Some activities need a single mind
• Sometimes, the elapsed time for an activity can not be shortened.
What happens to the project if a key person is sick or quits?

## Slide 19: Key Personnel: Schedule for Editor
Earliest Start Date Activity
Weeks 15-16 Edit Unit 3
Weeks 17-18 Edit Unit 4
Weeks 19-20 Edit Unit 5
Weeks 21-22 Edit Unit 6
Week 15 Review draft of Unit 7
Week 17 Review draft of Unit 8
Week 19 Check proofs of Unit 3
Week 21 Check proofs of Unit 4
Weeks 18-19 Vacation
Week 22 Out sick

## Slide 20: Start-up Time
On a big project, the start-up time is typically three to six months:
• Personnel have to complete previous projects (fatigue) or recruited.
• Hardware and software has to be acquired and installed.
• Staff have to learn new domain areas and software (slow while learning)
• Clients may not be ready.

## Slide 21: Experience with Critical Path Method
Administrative computing department at Dartmouth used the Critical Path Method for implementation phase of major projects.
Experience: Elapsed time to complete projects was consistently 25% to 40% longer than predicted by model.
Analysis:
• Some tasks not anticipated (incomplete understanding)
• Some tasks had to be redone (change of requirements, technical changes)
• Key personnel on many activities (schedule conflicts)
• System ZZZ (non-billable hours)

## Slide 22: Reading
Before next class, read the readings on Requirements that have been posted on the web site.