## Slide 1: CS 501: Software Engineering Fall 2000
Lecture 26
Risk in Software Engineering

## Slide 2: Administration: Laptop Return Times
Date: Wed Dec 6th
Time: 9:30 - 11:00 AM
Room: 5130 Upson
Date: Mon. Dec 11th
Time: 1:30 - 3:00 PM
Room: 5130 Upson
Date: Wed. Dec 13th
Time: 9:30 - 11:00 AM
Room: 5130 Upson

## Slide 3: Administration
• Examination
1.5 hours
5 questions
based on lectures
Objective is to reward those people who were regular in attending class.

## Slide 4: Failures and Risks
Software development projects can fail in many ways:
Bad software engineering
• Late, over budget
• Lack of function, full of bugs, bad performance
Changing circumstances
• Changing markets
• Better alternatives
• Changes of management
The biggest single source of problems is poor understanding of requirements

## Slide 5: Managing Risk
Manage projects to avoid risk:
• Open and visible software process
=> Avoid surprises
• Continual review of requirements
• Willingness to modify or cancel projects

## Slide 6: Canceling a Project
Example: Andrew Window Manager (wm)
• Technically superior to X (MIT's Athena project) in 1986
but ... Digital Equipment Corporation turning X into a product with massive support
nobody ready to support wm
• Therefore wm cancelled in 1986, Andrew user interface and applications ported to X

## Slide 7: Failure to Cancel a Project
Example: University F developed a novel programming language.
• From 1985 to 1989, this was a promising language for simple programming of window-based applications
• By 1990, clearly not gaining acceptance beyond University F
• But development continued for many more years (about $500K)
Not cancelled because ...

## Slide 8: Too Big to Cancel!
Example: University A has antiquated administrative systems. Senior management decides to replace them all with commercial packages from X. The timetable and budget are hopelessly optimistic.
• Staff get dispirited.
• The Chief Information Officer finds another job.
• A new Chief Information Officer is appointed.
What should she do?

## Slide 9: We are doing it the Wrong Way!
Example: University B has a (big) joint project with Company Y to develop a new computer operating system.
After two years work, a junior software developer persuades the university leader that the technical approach is wrong.
• What should the university do?
• What should the company do?

## Slide 10: How to Stop Gracefully
• It is harder to cancel a project than to start it.
• It is harder to withdraw a service than introduce it.
Considerations
• The proponents of the system must now reverse their public stance.
=> Management of expectations
• Users of the service need a migration strategy.
• Technical staff must have a graceful path forward.

## Slide 11: Time to Complete a Software Project
Large software projects typically take at least two years from start to finish
• Formative phase -- changes of plan are easy to accommodate
• Implementation phase -- fundamental changes are almost impossible
Yet many things can change in two years.

## Slide 12: A Sense of Urgency
Example: A not-for-profit corporation is developing a system for a government organization.
• By 1996 all research had been completed and the system demonstrated successfully with real users.
• In 2000, the system is still not in full production
Reasons:
=> Incremental improvements to the software
=> Repeated requests for more functionality
=> Reluctance to reorganize clerical staff
Nobody had a sense of urgency

## Slide 13: Overtaken by Events
Example: University C has a project to develop a digital library system, with funds from Company Z , private foundations and the government.
• By 1993 an extensive system is running at the university and Z is marketing the technology to its customers.
• By 1994 it is clear that web browsers and web formats (though technically weak) are becoming widely adopted.
=> What should the university do?
=> What should the company do?

## Slide 14: Changing Requirements and Design
Example: The CNRI Handle System -- a high performance, distributed system to map names to resources (1994-99).
• In 1994 only web browser was Mosaic
• In 1994 Java did not exists
• In 1994 mirroring and caching utilities were not available
• In 1994 commercial interest was limited
Design decisions made in 1994 had to be changed. Software was rewritten and greatly improved in 1998/9.
If a job's worth doing, it's worth doing twice!

## Slide 15: Changes of Leadership
Many projects are wasted because of management changes
Example: In 1988, Company W gave University D $1,000,000 to port a new operating system to its personal computers. The work was well done, on time.
• Company W changed its president and senior technical staff during the project. The work was wasted.
• A decade later and several presidents later, Company W is releasing a modern version of the same operating system.
A graduate student from University D is now Senior Vice President of Company W!

## Slide 16: Client Oversight
When work is out-sourced, the client must be vigilant.
Example: Company G was the world's leader in software for optimization (e.g., linear and integer programming). G had implemented several packages for various manufacturers.
• An operating system Company H contracted with G to develop an optimization package for its new operating system.
• The package was late, performed badly and disliked by customers.
What went wrong? What can we learn?

## Slide 17: Too Difficult!
Example: A development team at University E was given government funds to build a high-performance gateway from protocol x to protocol y.
• A promising young developer was hired and assigned to this task
• The project was too difficult for him, but he hid his problems for many months.
• The project produced nothing of value.
What can we learn from this experience?

## Slide 18: Engineering and Marketing
Corporate engineering & marketing divisions at cross purposes:
Examples:
• Xerox's Palo Alto Research Center pioneered window managers, Ethernet, graphical user interfaces, font managers, etc,
=> Apple, Adobe, Digital, etc. brought them to the market
• IBM would not bring its first Unix workstation to the market until the software had been largely rewritten
=> Sun's early workstations were unreliable but sold well

## Slide 19: Senior Management Dynamics
• Directors and shareholders appoint the President
=> The President does not want to admit failures
• The President appoints the Chief Information Officer
=> The CIO does not want to admit failures
• The CIO appoints the computing managers
=> The computing mangers do not want to admit failures
• The computing managers appoint the developers
=> The developers do not want to admit failure
Everybody pretends that things are going well

## Slide 20: Senior Management Dynamics
At last the troubles can not be hidden ...
• Directors and shareholders try to blame the President
• The President tries to blame the Chief Information Officer
• The CIO tries to blame the computing managers (and grumbles about the President)
• The computing managers try to blame the developers (and grumble about the CIO)
• The developers grumble about their managers
What can we do better?

## Slide 21: Sobering Thoughts
• Major computing projects are very complex. Inevitably there are delays and failures.
• Few organizations know how to manage risk & uncertainty.
• The best CIO's
=> Manage to minimize risk
=> Have the confidence of their staff who keep them truthfully informed
=> Have the self-confidence to keep their seniors truthfully informed