## Slide 1
Technical design aspects to be dealt with at headquarters are the standard parameters for typical work items. These standards encompass ranges of values within which the site engineer is allowed to operate. Design standards normally provide general guidelines relating to the following items:
• Location: Reference to places to be served and major obstacles to be avoided,
such as marshy areas, crops and difficult river crossings.

## Slide 2
• Alignment requirements: Instructions for setting out the course of the road.
• Technical performance: Specifications of maximum gradients, minimum
horisontal and vertical curvature, sight distances, super-elevation, cross-fall, etc.
• Materials requirements: Specification of the type, quality and method of
compaction, curing and tests to be performed.
• Structures: Recommendations on the use of local building materials such as
stone and timber, and on the design of bridges, culverts and road protection
works.
Road location and alignment are of particular importance when applying labourbased
work methods. High alignment standards aiming to reduce the number of
curves and soft gradients would require, particularly in hilly or mountainous terrain,
considerable longitudal earth movements which cannot be carried out economically
by labour.
Therefore, the site engineer should be aware of the need to select an
alignment where earth works are mainly lateral (cut to fill), and where horisontal and
vertical alignments will not lead to any significant longitudal haulage.

## Slide 3
Horisontal and Vertical Alignment
• Maximum grade
• Minimum horisontal radius
• Minimum vertical curvature
• Horisontal sight distance
Materials Data
• Soil or rock type
• Compaction and moisture content
• Curing requirements
• Aggregate gradations
• Mix proportions
• Strength requirements
• Tests to be performed

## Slide 4
Typical Cross Section
• Road width
• Maximum earth side slopes
• Pavement width
• Layer thickness
• Ditch details
• Width cleared of vegetation
Typical Structural Design
• River crossings
• Culverts
• Drifts
• Retaining walls
• Soil protection measures

## Slide 5
The design process as such deals with the following main steps:
• Establish road function.
• Assess the design traffic and its characteristics.
• Assess other factors which should affect the design (terrain, type of sub-grade, sub-grade strength, availability and cost of construction materials, etc.).
• Select geometric design standards (road cross-section, design speed and speed related standards).
• Select appropriate pavement design (total pavement thickness, thickness and type of materials for each component layer).
• Assess the need for road structures (bridges, culverts, retaining walls, etc)
• Assess the availability of labour in the vicinity of the road work sites.
• Assess the availability of local contractors.

## Slide 6
Parameter | Ref. | Class V F R M | Class VI F R M | Class VII F R M | ILO F M
Type of Terrain1 |  |  |  |  | 
Average Daily Traffic (vpd) 100-300 50-100 < 50 < 50 Design Speed (km/h) 60 40 20 60 40 20 40 30 20 30 Formation Width (m) a 7 7 6.5 6.5 6.5 6 6 6 5.5 5.5 5.5 Carriage-way Width (m) b 5.5 3.5 3.5 5.5 Shoulder Width (m) c 0.75 0.75 0.5 1.5 1.5 1.25 1.25 1.25 1.0 0 0 Cross-fall (%) d 3 - 4 8 Max Gradient (%) 7 8 9 7 8 9 8 9 10 10 Max Axle Load (tonnes) 9.1 5 |  |  |  |  | 

## Slide 7
Selecting the most appropriate road alignment is the most important part of any road planning and design process. If the wrong alignment is chosen, it can result in delays to construction works, over-use of resources and a road which is difficult and expensive to maintain.
The types of surveying work commonly demanded of road engineers and technicians are:
• rough topographical surveys preparatory to selecting routes,
• surveys of catchment areas preparatory to designing bridges and culverts,
• soil surveys to check adequacy of subsoils and quarry materials,
• more accurate surveys of the selected site or route to enable quantities of material to be estimated, and
• setting out of the actual works.
When surveying possible alignments for secondary and tertiary roads, it is often sufficient to drive a four-wheel drive vehicle along the proposed routes. The routes can be marked on large-scale maps, and the reading of the vehicle's oedometer can be used as a measure of distance.

## Slide 8
Best Crossing
Point
Intersection
Point
The aim of a topographical survey is to establish the most economical site or route for the proposed works. For a low-cost project such a survey would normally consist of a walk over the area of choice, noting possible alignments or sites, potential quarry sites, and soil conditions. A line level, linen tape and short tape are the minimum requirements for such reconnaissance work.

## Slide 9
The alignment should be selected to avoid areas of bad or difficult drainage, areas of bad soil or large earthworks, areas of rock outcrops or heavy bush clearing. In
addition, where drainage structures are needed, the road alignment should be selected so that the structures are located at the best crossing point.
Good location of the road alignment is the best way to reduce costs - try to avoid
areas that will consume a lot of workdays overcoming natural obstacles.
The alignment finally selected is often a choice between several alternatives. Each of these alternatives needs to be studied in detail, working out how they can be solved, and the amount of work and costs involved. For example, one could avoid an expensive structure by means of a longer route that went around the water course.
In this case, one would have to consider the cost of the structure against the cost of the increased road works.

## Slide 10
Engineers and technicians working on road projects may find the following notes on
design useful:
• Plan the route so as to minimise material movement.
• Select watershed locations and follow contour lines in mountainous terrain as much as possible.
• Plan the route to avoid numerous or large river crossings. Select crossings where
bridge construction will be simple or where ferry crossing will be possible at all
seasons.
• When shallow watercourses cross the route, consider the feasibility of a "submerged bridge" with pipe culverts, fords, or paved causeways.
• Consider proximity of suitable road materials when choosing the route.
• Avoid rocky areas and areas with heavy bush clearing.
• Locate the route so as to allow for future upgrading by realigning (e.g. easing of
curves and gradients) and widening.
• Plan sufficient passing places. The road stretch between the passing places should
be visible from both sides.
• If possible, clear the trees up to a distance back from the road equal to the height of the trees (more when the road runs east-west to facilitate drying after rain.
• Avoid two curves with a short straight in between. It is better to combine them into one long curve.

## Slide 11
• Avoid any horisontal curve at the top of or shortly behind a vertical curve where the driver will not be able to anticipate them.
• Avoid steep gradients. Try to keep longitudal gradients below 10%.
• Allow for adequate drainage. Poor drainage is the most frequent cause of failure of a road; a waterlogged road loses much of its load-bearing strength.
• Make drainage ditches wide and shallow. Wide drains allow water to run at lower speed than do narrow drains, which produces less erosion of the channel.
Also, wide drains are less easily blocked and more easily maintained than narrow drains.
• Be considerate with existing farming activities in the area. Avoid any situations
which may trigger soil erosion.

## Slide 12
The final centre line is first selected by means of a series of straight lines. These lines link together at points of intersection. The intersection points are located with the use of ranging rods, and properly marked by pegs. Once the intersection points are fixed, check with the local landowners to see if there is any objection to the proposed lines.
Pegs are used to mark the alignment and the levels of the road. They are made of wood and can be produced locally. They should have a length of approximately 40cm.
The chainage of the road is marked onto the pegs with a water proof marker.
Before construction works starts, reference pegs are placed outside the road formation.
Ensure that these pegs are hammered deep into the ground so that it will be difficult to remove them.

## Slide 13
Before the actual design work can begin, the engineer has to identify the possible technical problems of each works location. Assessment of the technical problems is an important part of the work of the engineers and technicians.
Special attention should be given to:
• drainage,
• horizontal and vertical alignment,
• soil conditions,
• structures needed, and
• sources of supply of materials and water.
The technical assessment of works to be implemented by labour-based methods
basically follow the same procedures as for machine-based methods. However, the use of labour-based methods should be taken into account so that:
• longitudinal haulage of earthworks is limited, and
• construction in weak soils and rock is avoided where possible.
It is important that the choice of alignment or location takes into account the technology that will be used. The engineer preparing the plans has to assess the problems and work out how to deal with them using the resources available.

## Slide 14
The technical assessment for the work should record the following information:
• design cross-section dimensions,
• existing vegetation cover,
• existing soil type and conditions,
• approximate earthwork quantities involved,
• design gradients,
• structures required,
• drainage measures required,
• gravel or laterite requirements,
• quality and sources of supply of laterite, crushed stone, water, etc.,
• quarry preparation work and hauling distances,
• required work force and availability of labour, and
• type and number of equipment items needed.

## Slide 15
When collecting information regarding the site conditions, it is important that it is
recorded in an organised manner which can easily be referred to at any time during the duration of the road works project. For this purpose, it is helpful to use a standardised form where the details of the envisaged works is recorded.
The "Proposed Road Alignment Sketch", is a form which records the initial assessment of planned works on a road construction project. In this form, detailed information can be recorded for any given section of the road.
Once the initial road alignment has been determined, the Supervisor and Engineer will carry out a survey of the road to estimate the amount and location of construction works.
Information about road curvature, earthworks (cut to fill, embankments, etc.), drainage structures (bridges, culverts, mitre drains, scour checks, etc.) is then plotted in the road alignment sketch at its exact chainage along the road alignment.

## Slide 16
When a final choice of the exact position of the road alignment has been made, the next step is to carry out a full estimate of quantities of work. The expected work quantities form the basis of the cost analysis and determine future inputs of labour, materials, tools and equipment.
Based on the information recorded in the road alignment sketches, it is possible to carry out a first estimate of the construction quantities. This form is more detailed than the Proposed Road Alignment
Sketch, since it records envisaged quantities of work on all future work activities. It
may therefore be necessary to re-visit the road alignment to carry out more detailed assessments of the quantities of work.
Based on these field surveys, the detailed information on volume of works is compiled in the "Estimate of Construction Quantities" form.

## Slide 17
ACTIVITY |  | Unit |  | KM |  |  |  |  |  |  |  |  |  | Total |  | Task rate |  | Workdays | 
 |  |  |  | 0-1 |  | 1-2 |  | 2-3 |  | 3-4 |  | 4-5 |  |  |  |  |  |  | 
SITE PREPARATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Clearing | m2 |  | 1700 |  |  |  |  |  |  |  |  |  | 1,700 |  | 75 |  | 23 |  | 
Stump and Rock Removal | No. |  | 6 |  |  |  | 1 |  |  |  | 2 |  | 9 |  | 4 |  | 2 |  | 
Grubbing | m2 |  | 3000 |  |  |  | 3000 |  | 3000 |  |  |  | 9,000 |  | 55 |  | 164 |  | 
Setting Out | m |  | 1000 |  | 1000 |  | 1000 |  | 1000 |  | 1000 |  | 5,000 |  | 50 |  | 100 |  | 
EARTH WORKS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Excavation to Level | m3 |  | 105 |  | 730 |  | 135 |  | 45 |  | 96 |  | 1,111 |  | 1.5 |  | 741 |  | 
Ditching & Sloping | m3 |  | 1075 |  | 165 |  | 748 |  | 725 |  |  |  | 2,713 |  | 1.6 |  | 1,696 |  | 
Forming Camber | m2 |  | 5500 |  | 5500 |  | 5500 |  | 5500 |  | 5500 |  | 27,500 |  | 80 |  | 344 |  | 
Watering and Compaction | m2 |  | 5500 |  | 6130 |  | 5500 |  | 6256 |  | 11800 |  | 35,186 |  | 90 |  | 391 |  | 
Reshaping | m2 |  | 5500 |  | 5500 |  | 5500 |  | 5500 |  | 5500 |  | 27,500 |  | 80 |  | 344 |  | 
EMBANKMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Fill less than 50 cm | m3 |  |  |  | 282 |  |  |  | 360 |  | 3041 |  | 3,683 |  | 1.8 |  | 2,046 |  | 
Fill over 50 cm | m3 |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  | 
GRAVELLING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Excavation, Load, Haul | m3 |  | 990 |  | 990 |  | 990 |  | 990 |  | 990 |  | 4,950 |  | by contract |  |  |  | 
Spread and Compact | m3 |  | 990 |  | 990 |  | 990 |  | 990 |  | 990 |  | 4,950 |  | 8 |  | 619 |  | 
Average Haul Distance | km |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | TOTAL |  | 6,470 | 

## Slide 18
Construction Targets
The setting of construction and productivity targets is essential for project monitoring.
The comparison between well established targets and actual achievement allows for a realistic judgement of the performance of a work unit or site. Targets must not only be set for outputs in terms of quantities, but also in terms of quality.
The degree of details of targets varies with the level of project organisation:
• at site level targets are established for individual activities,
• at field unit level only the summary or control targets for a number of sites are
required,
• at provincial level targets per field unit would be established and monitored, and
• at headquarters level the national and overall project targets are set and monitored.

## Slide 19
To be able to set targets, the following information must be known:
• the technical standards to be achieved,
• the quality standards to be achieved,
• the quantity and difficulty of the work,
• current task rates and productivity, and
• resources required and available (labour, materials and transport, etc.).
However, there are other factors that influence productivity and operational plans.
Some of these are beyond the control of the management, but must be allowed for:
• climate and rain seasons,
• cultural customs and traditional skills, and
• work incentives.
Once targets have been established, the planner can calculate the cost targets. The work plans may have to be revised in line with availability of funds.
Most projects will have a total plan, to achieve final project objectives, and annual plans to plan the work over a financial year.

## Slide 20
For operational planning only main targets are necessary, such as:
• workdays per km,
• cost per km,
• number of km completed
Time Management Planning
Construction timing is an important part of operational planning. Generally, two
planning phases are used - a long term planning phase (annual work plan) and short term planning phases (monthly or weekly work plans).
Annual Plan
The annual plan is prepared by the Provincial Engineer at DCTPC in consultation with
the management at Ministry level. The list of priorities and the assessment of work
quantities provide the data required for preparing the work time schedule.
Generally, the annual work plan will contain the following:
• name and location of the works,
• target quantity of work for each works location,
• type of work by works location,
• workdays and equipment-days (targets) for each works location,
• starting and finishing month for each works location,
• estimates of cost for each works location, and
• summary totals.

## Slide 21
Construction Sequence
Once the site camp has been established and supplied with materials, tools and
equipment, the road construction works can commence.
Road construction works are divided into a number of operations, each sub-divided into a series of activities. The separate operations on a construction site have to follow each other in a logical sequence. The table below gives a general view of the works sequence on a road construction site:
Operation | Activities
Support | work at site camp, setting out alignment
Site Clearing | detailed setting out, bush clearing, grubbing, tree and boulder removal
Earthwork | excavation and filling, spreading and levelling, drainage and camber formation, embankments
Compaction | watering, compacting and final levelling of earth works
Structures | drifts, culverts and small bridges
Gravelling | excavation and transport of gravel, un-loading, spreading, watering and compaction

## Slide 22
Daily Work Planning
A supervisor must always plan ahead by at least one day. After the
workers have completed their daily work, the supervisor records the
outputs achieved on each of the activities. Based on the production
achieved and the overall plan for the project, a plan for the following day
is prepared. This plan sets the daily production targets for each of the
planned activities.
To prepare these work plans properly, the supervisor needs to know what
has happened on the site before. Without information such as what
resources were needed to produce a given output, why certain targets were
not met, etc., proper planning is impossible. To get the right information on time, a well functioning reporting system is required

## Slide 23
Gang Balancing
Balancing of gang sizes, i.e. ensuring that the labour is used in the most efficient way, and that each of the operations on average proceed at the same pace, is the daily task of the site supervisor. The size of the gang will vary according to the work being undertaken, and depends on:
• the amount of work to be done on each operation,
• the task rates being used,
• the available labourers, and
• the sequence of operations.
Good gang balancing is important because it also determines the length of the
construction site. If the gangs are not well balanced, the result may be that the work site spreads out and becomes to long to supervise in an efficient manner, or that it becomes to concentrated and the workers are working in a small and congested area.
The amount of work will vary along the road line. Therefore there will be a demand
for adjusting the number of workers in each gang.

## Slide 24
Control of Works
The supervisor needs to inspect and approve the work before the workers are released for the day. He/she should be notified by the gangleader, who informs him/her that a particular task has been completed and is ready for inspection.
If the work has been satisfactorily completed, the group or individual may be released for the day.
If the work is not complete, it should be corrected before the group or individual worker is allowed to leave the site.
If the task is not completed before the end of the normal working
day, the supervisor needs to find out the cause of the delay -
whether the cause lies with the workers or with his/her own setting of the task.
If the reason for non-completion is one of the following, the workers should be
released:
• major difficulties were not envisaged when the task was set (i.e. heavy roots, big rocks, etc.),
• incorrect measurement or calculation of the task,

## Slide 25
Site Camp
Before road construction works can commence, a site camp needs to be set up to accommodate the supervisors, materials, tools and equipment. The site camp needs careful planning to provide site staff with a basic comfort, and adequate storage and security for equipment and materials.
Location
The selection of a suitable camp location should be made by the supervisor and the engineer. The following items should be taken into consideration:
􀀹 it should be close to the construction site, preferably in walking distance,
􀀹 it should have access to drinking water,
􀀹 it should be located on high, well-drained land,
􀀹 it should have sufficient space for parking equipment after working hours, and
􀀹 it should be easily accessible to project vehicles bringing equipment and materials.