## Slide 1
The size of the camp depends on the size of the project, what type of works will be
carried out and how far the site is located from headquarters.
In most cases, the site camp can be set up in a local village through which the road will pass. Then, suitable accommodation and stores can be rented from the local villagers. In more remote places, the entire site needs to be established by the project.
Standard requirements for a site camp are:
􀀹 accommodation for the supervisors and equipment operators,
􀀹 a site office,
􀀹 a site store,
􀀹 appropriate cooking facilities,
􀀹 toilet and bathroom facilities, and
􀀹 extra site store for fuel, oil and lubricants.
For a road construction project covering more than 7 to 8 kilometres, the camp will
probably have to be moved once, twice or even several times. These moves have to be planned well in advance so that the necessary transport can be arranged.

## Slide 2
Handtools
Tool requirements depend on various factors such as the size of the project, soil types, terrain and the type of works which are planned. The below table indicates the required hand tools for a project employing a labour force of 100 workers or 200 workers.
Item | 200 workers | 100 workers
Profile Board Ranging Rod Hoe Hoe Handle Shovel Spade Pickaxe Pickaxe Handle Crowbar Bush Knife Axe Bowsaw Grass Slasher Heavy Duty Rake Hand Rammer Wheelbarrow Sledge Hammer Bucket Watering Can Fuel pump 30m Measuring Tape 3m Measuring Tape Line Level Nylon String | 100 100 150 150 75 30 75 75 10 10 15 7 15 40 25 60 3 10 10 1 3 3 3 300 m | 70 70 70 50 50 20 25 25 5 5 5 4 10 30 20 40 3 8 8 1 3 3 3 300 m

## Slide 3
Maintenance
Ensure that the tools on site are in good order, that the tools are sharp and that the
handles are firmly fitted and not damaged. When you find damaged tools on site, report this to the store keeper and have them repaired or replaced immediately. This will increase work efficiency and enable the workers to complete their task work on time.
On large projects, it may be useful to employ a person to maintain and repair handtools.
Alternatively, it is always useful to check with the local villagers if there are any
blacksmiths or carpenters available in the neighbourhood.
Make sure that the camp is equipped with effective sharpening tools and a sufficient
supply of spare parts. The tools required to carry out routine maintenance are cheap
and simple to use.
The cutting edges of axes, hoes, mattocks and grass slashers are normally sharpened
with wet-stones. The edges of other cutting tools are best kept sharp by a selection of
flat, half round and round files. For saws, small triangular shaped files, with a side
about twice the depth of the teeth are appropriate.

## Slide 4
A simple vice should be available at the site store to enable the store keeper to work efficiently.
A vice will enable hand tools to be firmly gripped when maintained or
repaired.
Have a sufficient supply of spare handles on site. A loose or damaged handle is dangerous and should be fixed immediately. Purchase good quality handles made of hard wood which are properly designed according to established standards.
Do not rely on makeshift handles made locally on site.
Wheelbarrows need a lot of maintenance to remain serviceable. Each day, all bolts and nuts should be tightened.
If a bolt is lost, it should be replaced before the wheelbarrow is used again. If the wheelbarrows have pneumatic tires, supply the store keeper with a pump and patching equipment.

## Slide 5
Storage
Tools are issued by the store keeper to the workers every morning and returned in the
afternoon after completion of works. Ensure that the workers are issued the correct
type of tools according to the work activity they will be carrying out. The store keeper
is responsible for keeping full records of the tools and controlling the daily issue of
tools to the workers. The total amount of tools on site needs to be counted regularly
and reported back to headquarters.
The size of the store depends on the amount of tools to be stored. When the road site is very isolated, the store has to be well stocked and therefore tends to be larger in size.
Tools should be stored in a dry and secure place. Stock the items neatly so that they can easily be counted.
Stock different items separately and stock items of different sizes separately.
If necessary, employ a watchman to guard the stores when the storekeeper is off duty.

## Slide 6
Each piece of equipment has an Operators Manual, which specifies when and where lubrication and adjustments are required. As a rule of the thumb, the following activities should be carried out on a daily basis:
Clean and Check
􀀹 lubrication oil level
􀀹 radiator water level
􀀹 hydraulic oil level
􀀹 hydraulic hoses and couplings
􀀹 grease nipples/tracks
􀀹 battery terminals and battery water
􀀹 connections from alternator
􀀹 all the V-belts and their tension
􀀹 tire pressure/tracks
􀀹 transmission oil level
􀀹 brake and clutch fluid level
􀀹 nuts and bolts of buckets and tracks

## Slide 7
Materials
Supply of materials should be made well in advance of its planned consumption. Ensure that sufficient materials are available on site before commencing the works for which the materials are planned. Also, notify the engineer in good time when stores need to be replenished.
When materials are received on site, it is the responsibility of the store keeper to inspect and verify that the stores are in good order and correct quantity. Finally, the materials are recorded in the stores ledger.
Fuel, Oil and Lubricants
Fuel, oil and lubricants should be stored separately, away from the other supplies. These items can be a fire hazard, if not treated properly. Make sure that there are no open fires nearby, such as fire places for cooking, etc.
Fuel is normally stored in drums. Make sure that all consumption of fuel, oil and lubricants are properly recorded and accounted for.

## Slide 8
Culvert Rings
Culvert rings are normally stored at the road site at the planned location of the culvert. They need to be handled with care, in particular when off-loading to avoid that they break. When ordering culvert rings always order a couple of spare rings in case of breakage.
Cement
Cement is very expensive, so it must be handled and stored with care. Avoid breaking the sacks when handling and keep it in a dry and flood secure place. Stack the cement bags off the floor. Always use the oldest cement first.
Pegs
Wooden pegs for the setting out activities are normally produced on site. They should be made well in advance so that the sites have sufficient supply when they are needed. Production of pegs should be organised under the responsibility of the store keeper. If necessary, an additional person can be hired for the collection of wood and cutting of the pegs.

## Slide 9
The Basic Principle of Setting Out
Acommonly used setting out procedure is based on the use of a series of profile boards and a string line level giving control of levels during construction. As a result, the method has become known as the "Profile Board Method".
The basic principle when using profile boards is that when we set them out we are putting up a series of level boards that show us the level 1 metre above the completed construction levels. With practice, it becomes easy to work with these tools and roads can be built properly, economically and at high quality standards.
To ensure that we obtain the correct level in the ditch, we would put up profile boards at positions A and B, 1 metre above the level we want the ditch to be:

## Slide 10
Traveller
We need a third profile board that we can move around. It is known as the travelling profile or traveller. Along the line from A to B, we excavate slots to the level of the ditch. If we place the traveller in a slot and sight from profile board in position A to the profile board in position B, we can see if the traveller lines up with the two fixed profile boards. If the traveller is too low, the slot has been dug too deep. If the traveller sticks up above the sight line, the slot needs top be dug deeper.
To provide good guidance, slots are dug at regular intervals, say at every 4 to 5 metres along the sight line.
When sufficient slots have been dug, the workers can start excavating the ditch by joining up the slots. The traveller can then be used to check that the finished work is to the correct level and that there are no high or low spots.

## Slide 11
0.6 0.6 5.5
This section describes step by step the setting out the road camber of a road
section in rolling and hilly terrain. If the road needs to be elevated on an embankment, refer to the section covering Embankment Construction in Module 5 Construction Procedures.
Normally, the road camber is set out together with the side drains. Once the position and levels of the centre line has been determined, it is possible to construct the camber and side drains.
Notes: <number>

## Slide 12
When setting out the road camber and side drains, it is important to reduce the amount of excavation to a minimum by following the existing level of the terrain along the road line. The procedure described below is an efficient way of setting out the road levels, achieving a well placed road with good drainage and which does not involve massive excavation and/or fill works.
Step 1: Using the previously set out centre line, set out ranging rods at 10m intervals along the centre line for a section of 50 to 100 metres. At the start of the section, measure out the position of the road shoulders and the outer end of the side drains from the centre line. Repeat this exercise at the other end of the section.
Place a wooden peg next to each of the ranging rods.
Step 2: Once the key positions of the road has been set out at the start and the end of the road section, sight in intermediate ranging rods at every 10m along the road shoulders and side drains.

## Slide 13
Step 4:
Go to the centre line ranging rod at the other end of the road section and repeat the procedure, measuring up 1m from the ground level.
Step 3:
On the centre line of the road, fix the first profile board. This profile may be already in position as the last profile from the previous setting out. If not, measure 1m up from the existing ground level, and mark this level on the ranging rod. Fix a profile board to the ranging rod so that the top edge of the profile board is at the mark made on the rod.

## Slide 14
Step 5: By sighting in the intermediate profiles from one end, fix profile boards on the
intermediate ranging rods along the centre line so that they are all at the same level.

## Slide 15
Step 6: Check the height of each profile board above the ground level. If the height is
approximately 1m, there is no need to adjust them and you can use the level of the profile as it is.
If the height of the profile boards is greater or less than 1m by 10cm, then inspect the line. There may be humps or depressions along the line. The set out line will in most cases smooth out these variations. However, it may be that the set out line is over a hill or a dip in the terrain. In such cases
in the two figures below.
Adjust the profile at position D so that it is 1m above the ground and then lift the profiles at B, C and E to sight in line with the profiles at A to D and D to F. This exercise will reduce the amount of excavation works.

## Slide 16
General Rules
1. It is better to lift profiles than to drop them.
2. Try to keep lifts and drops less than 10cm.
3. Try to match the road levels to the terrain.
4. Use the profiles to get a picture of the vertical road alignment.
.
Before starting on the next step, make sure that the side drains can be emptied. It is important to spend time on this step to get the levels right. All other levels will be set out based on the profiles along the centre line of the road.
Step 7:
Transfer the levels to the ranging rods at the outer end of the side drains. Start with
the beginning of your road section. Using a string and a line level, transfer the level of the profile board at the centre line to the ditches on the both sides of the road. Once the levels are set out with profile boards, mark the levels on pegs next to each ranging rod.
Repeat this procedure for the same two ranging rods at the other end of the road section and for any intermediate profile along the centre line that was lifted or
lowered to reduce excavation works. Then, sight in the intermediate side drain levels.

## Slide 17
You will notice that the height of the drain profile on the low side of the centre line is more than 1m in most cases. This is because we have started from higher grounds, and since the road is level, the lower side drains will be less deep.
Step 8:
Mark the levels for the centre line on pegs placed next to the ranging rods along the centre line. Now use the centre line profile boards to set out intermediate pegs placed at every 5 m along the centre line. This is easily carried out with a 1m traveller. Mark these pegs at the point where the bottom of the traveller touches the peg, when lined up with the profiles. On all the centre line pegs, mark the level of the crest of the camber 0.25m above the 1m level on the pegs.

## Slide 18
Step 9: Place the levels of the shoulders along the road. For this, it is useful to have a traveller 1m high. If we line up the traveller along the line between the two side drain profiles, the bottom of the traveller will show the correct level of the shoulder.
Place pegs every 5m along the edge of the shoulder, and using the traveller, mark these pegs at the point where the bottom of the traveller ends when it lines up with the profiles.
Step 10: Locate and set out the mitre drains. It is important that the mitre drains are set out before the excavation works for the side drains and camber is commenced.
Step 11: Set out with string line the side drains that needs to be excavated. Remember to leave out the mitre drain block-offs.
Notes: <number>

## Slide 19
CLEARNIG
Heavy bush clearing involves cutting down and removing trees, the clearing of
dense bush and scrub and the digging up and removing root systems to
prevent regrowth.
Boulder Removal
Boulder removal can involve hand carrying small boulders, rolling clear, breaking or digging and burying large boulders.
Topsoil Removal
Topsoil removal is usually only needed where the topsoil is deep (10-15cm), very organic and obviously much lower in strength than the soil below. Unnecessary topsoil removal has very little effect on the strength of the road. Topsoil removal is most likely to be needed in river valleys and flood areas that build up silt.
Most agricultural land and open areas are eroded, with a very thin topsoil layer which can
be mixed in with the earthworks for the road construction.
Topsoil removal is executed using task work on an area basis, the area being
determined by the thickness of the topsoil.

## Slide 20
Earth Work
Basically, road construction earthworks involves digging drains and using the
material to build up the camber, excavating cut to fill to form the road and
building up the road on embankments in flat areas with poor drainage.
The earthworks is then simply to excavate the side drains and use this material to form the camber. Ensure that the volume of the side drains is slightly more than what is needed to form the camber. Usually more material is needed than indicated, either because of low spots in the ground or because of unsuitable soil or because the land is never consistently level.

## Slide 21
Cut to Level
The challenges really begin when the road is built on cross sloping ground. The
steeper the cross slope, the more excavation is needed to build the road. Always
avoid steep cross slopes where possible. Locate the road on ridges where possible -
this will reduce earthworks as well as reduce drainage works.
Road construction in cross sloping terrain have the following features:
• the high side drain will have to be dug deep,
• the low side drain is normally not needed, and
• the road will have to be built on a fill on the low side.
The best way to do this is to split the work into two separate stages.

## Slide 22
Stage 1: Excavate the high side and build up the low side and form the
side slope on the low side.
Stage 2: Excavate the high side drain and form the camber.

## Slide 23
The advantages of this method of working in stages are:
• the excavation approximately balances the amount of fill needed,
• the fill material can be obtained as close as possible to where it is needed - reducing the need for longitudinal haulage,
• by levelling the formation only as far as the edge of the road and then sloping down to the natural ground, reduce the excavation and, in most cases avoid the
need for a side drain on the low side.
The excavation and fill are balanced each side of the centre line, but the width of the excavation has to give sufficient room for the side drain to be dug. This fixes the setting out dimensions for excavation on the high side.
Example:
Assuming a road carriage width of 5.5 m and a side drain width of 1.5 m, the total levelling width on the cut side of the centre line would be:
5.5m / 2 + 1.5m = 4.25m

## Slide 24
Day 3 Day 2 Day 1
When the centre line profiles are set out at 1m above ground level, we can measure
the height of the high side profile to tell us:
✔ how steep the slope is,
✔ the depth of the cut, and
✔ the volume of the levelling works and back-sloping.
Notes: <number>

## Slide 25
When there is little cross slope (the average height of the high side profile is 90 or
95cm), it is possible to dig the high side drain without levelling first. However, there
are advantages to levelling in these conditions. Setting out the side drain is easier on
a levelled surface and the side drain easier to build to the correct shape. The
supervisor will usually level these minor cross slopes.
The setting out in these cases will be different as there is no advantage in levelling
right through to the centre line. The levelling would then be done from the road
shoulder to the outer side of the side drain (from 2.75m to 4.25m, measured out from
the centre line in the example above).

## Slide 26
Please note that the above levelling practice only applies for new construction. When
rehabilitating an existing road, levelling works should be kept to a minimum, leaving the existing road camber in place and only adding onto it where it has been worn down.
We can calculate the volumes to be excavated for the most common profile heights to be found in practice. These volumes can be given to the supervisor in table form and can be used to work out the workdays needed to carry out the excavation and are used to report the volume of completed works.
The slope of ground is not the same along the length of the road. To set out the work we have to find the average slope over a 20m section.

## Slide 27
Camber and Side Drain Construction
Once the excavation and fill have been completed, the road camber is constructed using soils from the side drains and back slope. Excavated soils from the drains should first be thrown to the centre of the road, from where it is levelled out towards each road shoulder to form the camber.
Side drain excavation is done in two stages. First the ditch is excavated, then the side slopes of the ditch is excavated. Normally, one or two days are allowed between each stage to allow sufficient working space for the workers.
The side drain excavation is set out using string line and pegs, and controlled by using ditch templates.

## Slide 28
For both ditching and sloping, tasks are set as a length of the side drain for each worker. The sloping task is normally set slightly higher than the ditching task, because excavation of soil on the slope face is easier to carry out than excavating the ditch.
The soils excavated from the side drains are used to construct the road camber. To achieve an exact and properly levelled camber, the work is set out using pegs and strings.

## Slide 29
Once the soils for the camber has been levelled, the camber is properly compacted. Make sure that the soils contain optimal moisture content.
After compaction has been completed, it is important to check that the final levels of the road camber is exact and to the prescribed standard and quality. This can either be done by setting out the profile boards again and controlling the level between the profiles with a traveller. A quicker method, however less accurate, is to use string lines to check the level of the completed surface.
If the levels are in-accurate, the irregularities should be removed or filled in. If further filling is required, make sure that this patching is also properly compacted. Finally, repeat once again the checking of the levels to ensure that the earthworks are completed to the correct standards.

## Slide 30
Embankments require large amounts of fill material and are expensive to
construct. They should be avoided when possible by selecting a longer route on higher ground. However, this is sometimes not possible in low, flat, agricultural land, where often no alternative route exists.
Wherever possible, material should be excavated alongside the road and carried to the road by baskets or wheelbarrows. If land is not available for roadside borrow pits, or if the material is not suitable, then earth will have to be brought in from the nearest source by appropriate haulage transport. The type of the borrowed soils should be of good quality. Organic soils, and if possible, sand and silt should be avoided. If sand or silt are the prevalent materials in the area, side slopes should be protected with at least a 15cm layer of clayey soils and vegetation to prevent erosion.
It is important to keep the height of the embankment to the least requirement. This is normally considered to be 0.5m above normal flood levels.
Highest annual flood levels are used to determine the embankment height. This information should be available from local inhabitants and should be marked on pegs along the centre line when choosing the alignment.
Centre line alignment should be carefully selected to avoid low lying areas requiring extra fills and areas where suitable material is not available from the roadside.
The below figure summarises the key dimensions of the cross-section of embankments utilised in the ILO labour-based road works project.

## Slide 31
Earthwork Volume Calculations
Calculation of earthwork quantities is especially important for the planning and control of embankment construction operations. It is necessary to apply a simple and accurate method of estimating embankment quantities at site level.
The standard cross-section dimensions are fixed by national or programme
specifications. In this example, we will assume the dimensions used by the ILO project, i.e. a road width of 5.5m, side slopes of 1:2 and a clearance above highest flood water level of 0.5m.