## Slide 1
The Global Learning Connection
Leading Change Initiatives
Materials Adapted for Use by CARE With Permission from Gary D. Jewkes & Associates. 2002

## Slide 2
Objectives
Understand change framework and concepts
Understand how to apply to your own change initiatives
Identify and begin to practice change agent skills and competencies

## Slide 3
A Change Experience
Individually, think of one successful or unsuccessful change effort you were involved in and describe the characteristics of change you observed.
Then, in small groups, share your experiences and develop a group list of requirements for successful Change initiatives.
What must be present in order for the Change to be successful?

## Slide 4: CHANGE GOAL
Technical Plan “T”
Culture, People, Organizational Commitment, Political Plans “C”

## Slide 5
How it all works together
T x C = E (Effectiveness of Change)
C
T

## Slide 6
Why A “Change Leadership Model”?
Accelerates and focuses change
Provides a common language
Engages managers in “living the change” rather than “delegating it”
Provides a simple checklist and tools

## Slide 7
CURRENT STATE
TRANSITION STATE
FUTURE
STATE
1. Leading the Change
2. Framing the Shared Need
3. Describing the End State
4. Mobilizing Commitment
5. Identifying Systems and Levers for
Alignment
6. Communicating the
Change
Tracking Progress
Define
the
Change
Develop a
Detailed
Implementation
Plan
Step 1
Step 2
Step 3
Leading Change Model

## Slide 8
LEADING CHANGE MODEL
Leading the Change Exhibiting leadership behaviors that clearly signal the need and vision for this change; leading the team through all the change processes.
Framing the Shared Need Making certain there is a commonly shared reason for change that is greater than the reasons for “staying the course” – the “Business Case”.
Shaping the Vision Creating a vision of the change initiative that is compelling, simple, and behavioral. This vision answers the question: “What will it be like when this change is successfully implemented?”
Mobilizing Commitment Identifying pockets of resistance and support from all key stakeholders. Ensuring that a plan is in place for bringing all stakeholders, “on board.”
Identifying Systems and Levers Shaping, altering and employing the systems and processes inherent in the organization to effectively support change efforts.
Communicating the Change – creating and sending the right messages, from the right senders at the right times so as to constantly inform and build support for the change amongst the target population.
Tracking Progress Connecting the change to organizational results & making sure that progress is real. Establishing “baseline” measures and milestones

## Slide 9
Leading Change: Process Profile
0
5
10
Leading
Need
End-State
Mobilizing
Aligning
Communicating
Tracking
Evaluate a current change initiative against each of these elements.

## Slide 10
CURRENT STATE
TRANSITION STATE
FUTURE
STATE
Define
the
Change
Step 1
Step 2
Step 3
Leading Change Model

## Slide 11
Defining the Change
What is the current state of the organization or audience that indicates a need for change? What are the issues/problems?
What is the Future state of the organization or audience that you would like to achieve?
Of all the various projects and initiatives that might contribute to achieving that future state – which one are you going to work on?
Have you identified/defined your change initiative so that it:
  Has a clear beginning and end
  Is within your sphere of influence/control
  Is based on an organizational or business priority

## Slide 12
CURRENT STATE
TRANSITION STATE
FUTURE
STATE
Describe the current, transition and future state in the boxes below
Scoping the Change Worksheet

## Slide 13
In leading any initiative, team members will be expected to simply state what it is they are working on or doing. The purpose of this worksheet is to create one or two sentences using 15 words or less that describe your change initiative. Please draft your statement below.
Change Initiative Name: ________________________
The __(initiative name)__________ is __(state the action the initiative will do)____________________
__________________________________________________________________.
The reason we are doing this is _______________________________________
__________________________________________________________________
__________________________________________________________________
And, as a result, we expect to achieve __________________________________
__________________________________________________________________
__________________________________________________________________
Change Definition Statement Worksheet

## Slide 14
CURRENT STATE
TRANSITION STATE
FUTURE
STATE
1. Leading the Change
Define
the
Change
Step 1
Step 2
Step 3
Leading Change Model

## Slide 15
LEADING THE CHANGE
OUTCOMES
The Change Initiative Team is defined: the Sponsors, Change Agents, Resource Teams and Change Targets
The roles are defined and a plan is in place for explaining to each team category what their role is, why it is important and how their support is important for the Change Initiative success.

## Slide 16
Leading the Change
Who will provide the critical sponsorship for your project?
2. Who will be the change agent and / or champion and do they have a clear contract with the sponsors?
Who will implement the changes that are planned?
In what way will other managers / supervisors be affected by or involved in this project?
What other leadership support and involvement is needed?
6. How will you demonstrate your ongoing commitment to this change effort? Do your actions signal your commitment to change?

## Slide 17
“MORE THAN
80% OF ALL CHANGE
EFFORTS FAIL”
David Smith Taking Charge of Change

## Slide 18
Successful Change Management
“Overwhelmingly, participants cited executive sponsor participation as the single greatest contributor to the success of their change management program.”
Prosci’s Change Management
Best Practices Study 2000

## Slide 19
Change Process | Change Sponsor | Change Agent | Change Target
Leading Change | Supports and builds consensus for change vision | Champions Change | Makes Change
Framing the Shared Need | Questions status quo: encourages risk taking | Builds case for changing status quo: takes risks | Defies status quo: absorbs risks
Describing the End-State | Integrates change with strategy | Translates change to be consistent with strategy | Makes changes to ensure fit with strategy
Mobilizing Commitment | Shares ownership: involves others: buffers upper-level conflicts | Accepts ownership: networks with others: resolves conflict | Owns change: informs others: manages day-to-day conflicts
Aligning Systems, Structures, and Levers | Works to design and align systems and structures | Makes systems and structures practical and real | Implements new systems and structures
Tracking Progress | Monitors results: shares credit | Measures results: receives credit | Achieves results: earns credit
Developing the Road Map | Provides resources for change: integrates change initiatives. Removes barriers | Assigns resources: persistently pushes change initiative | Uses resources: gets results, implements change initiatives
CHANGE TEAM ROLES

## Slide 20: TYPES of TEAMS ESSENTIAL for the SUCCESS of the CHANGE INTITIATIVE
Leader Roles
.
Sponsor
Team
x
x
x
x
x
x
x
x
x
x
x
x
x
x
x
Change Agents
R
R
R

## Slide 21
THE CHANGE TEAM-- Systemic & Holistic Approach
.
Sponsor
Team
x
x
x
x
x
x
x
x
x
x
x
x
Change Agents
R
R
R
Change
Targets

## Slide 22
a. Technical experts for each “piece” of process
b. “Clients/Customers”(internal/external)
c. “Partners/Donors”- (Input to process)
d. Functional/Stakeholder Representatives
e. “New” and Experienced in the subject matter or processes
f. Cross-functional, Multi-level Stakeholders, Diverse
BUILDING THE CHANGE TEAMS
As you determine the composition of your change initiative CO team. Make sure you are considering those individuals who will have a significant impact on the outcome of the change initiative. Consider those who are:

## Slide 23: Effective Team Characteristics
Effective teams:
Own a shared and meaningful purpose and vision
Agree on specific goals
Clearly identify team member roles with the realization that the roles are interdependent
Participate in a common, collaborative approach to decision making
Hold team members accountable for their work as it contributes to the entire team’s results
Pay attention to both the “what” that needs to be accomplished as well as the process of how the team works together
Demonstrate passion , pride and a commitment to team work
Learn from their experiences and embrace the challenge of learning new things

## Slide 24
Role Of The Sponsor
A Clear Charter of Responsibilities Sets Up the Team For Success
• What processes are the team responsible for and why are they are important to the organization?
• What requirements or boundaries are given for this team?
• What is the reporting relationship to the sponsor?
• What authority to act or decision making power does the team carry?
• On what issues is the team expected to consult or inform the chartering agent?
• What deliverables are expected? What milestones and time lines?
• How will the team be measured?

## Slide 25: Sponsor’s Contracting Suggestions
* Provide Support:
1. Financial
2. Staff
3. Verbal
4. Feedback (all levels, positive and constructive)
5. Be visible
* Represent changes at all levels:
1. Attend meetings, be involved
2. “2 minute Brief”
3. At team meetings with peers and manager
* Provide access:
1. Change agent with sponsor team
2. Change agent with management i.e., two levels above or more
* Build consensus with:
1. Sponsor’s team
2. Sponsor’s boss
* Review contract on a regular basis
* Incorporate into performance objectives:
1. Key performance measures
2. Recognition & Reward

## Slide 26: Contracting Suggestions
Change Agent may agree to:
  Ensure sponsor input
  Provide clear statements of need and end-state
  - Benefits
  - Data
  Schedule feedback, summaries and updates - Share both positive and negative information
  Provide feedback
  Cost benefit analysis
  No surprises

## Slide 27: Team Composition Worksheet
Team Composition
Sponsor Team:
Categories
Members
Change Initiative Team
Categories
Members
Resource Teams:
Categories
Members
.
Sponsor
x
x
x
x
x
x
x
x
x
x
x
x
x
x
x
x
Change Agents
R
R
R
In the spaces below - identify the categories of stakeholders that should be represented on the team. Also, identify and list specific individuals to invite to be team members

## Slide 28: Team Charter Worksheet
Describe the initiative’s desired results and whose support you need: The specific activities or accomplishments; The clear and measurable outcomes; Who takes ownership of which pieces
Explain what the project includes– and what it it does not include: “Do’s” and “Don’ts,” boundaries
The kind of resources you will need to do this effectively and sustain involvement: Human, financial, technical, and organizational resources needed.
Explain your plan for accountability and deliverables: Measures, due dates, schedule of assignment, and responsibilities
Explain the consequences of achieving or not achieving agreement.
Extrinsic and intrinsic “win” for the team and organization benefits, risks, and costs.

## Slide 29: Sponsor Contracting Worksheet
List the specific types of support the team will need from the Sponsors:
List the specific types of support/actions the team agrees to provide to
the Sponsors (i.e. regular information/updates/deliverables):

## Slide 30
CURRENT STATE
TRANSITION STATE
FUTURE
STATE
1. Leading the Change
2. Framing the Shared Need
Define
the
Change
Step 1
Step 2
Step 3
Leading Change Model

## Slide 31: FRAMING THE SHARED NEED
OUTCOMES
A shared belief among critical stakeholders that there is a clear need for change, based on its importance for business results; that it is critical for both the organization and for individuals, and that the need for change is greater than the resistance.
A “Business Case” that answers the question, “Why?”. “What is the driving force for change?”

## Slide 32
Framing the Shared Need
Who are the Key Stakeholders and what are their Needs/Concerns with regard to the change
2. Have you developed “framed” a compelling need statement to appeal to each stakeholder group
Is need for the change greater than the resistance?
Have you provided data and demonstration to support need?

## Slide 33
Stakeholders
Anyone who has an interest in the process or outcome
Anyone who may need to support the change
Anyone who casts a “vote” on your success
May be an individual, group, organization, etc.

## Slide 34
WORD EXERCISE
You will be assigned a specific word that everyone understands. You will be given 60 seconds to write down as many words possible (at least 10) that you associate with the assigned word. Before the exercise starts, however, your team should estimate the number of word “matches” that all team members share from their lists.
Round One:
Assigned Word:___________
My List
_
_
_
_
_
_
_
_
_
_
Team Goal for Matches:______________
Actual Matches: _____________________
Round Two:
Assigned Word:___________
My List
_
_
_
_
_
_
_
_
_
_
Team Goal for Matches:______________
Actual Matches: _____________________

## Slide 35: Threat/Opportunity Matrix
Threat
Opportunity
1
Short Term
Long Term
2
3
4
Your Change Initiative is in one of these quadrants. How do you express the “need” to support the initiative to your different stakeholders?

## Slide 36: FRAMING THE NEED - PROVE IT!
Approaches… | Examples…
Data: - Existing data - Benchmark data - Data to be gathered | 
Demonstration: - Best practices - Symbolic demonstrations - Examples or demonstrations | 
Demand: - Dynamic leadership - High standards - New Leader Behavior | 

## Slide 37: Identify key stakeholders or stakeholder groups for your change and then consider their likely view point regarding your initiative. Identify those issues or concerns that are relevant for that stakeholder group. Eventually you will “frame” your need statement to address the key stakeholder concerns.
Stakeholder
Stakeholder Issues/ Needs
Framing Stakeholder Needs Worksheet

## Slide 38
CURRENT STATE
TRANSITION STATE
FUTURE
STATE
1. Leading the Change
2. Framing the Shared Need
3. Describing the End State
Define
the
Change
Step 1
Step 2
Step 3
Leading Change Model

## Slide 39: Describing the End-State Outcomes
A clear description of the outcome of the change effort, articulated in both emotive (visual, enticing) and pragmatic (numerical) ways. What our “new world” will look like- the new Paradigm and the new actions and behaviors it will require.
End State Description = Motivation + Direction

## Slide 40
Shaping the Desired End State
What is your broad vision about your new “end state” or desired outcome of the change initiative?
What will be the benefits of this change to the organization, to stakeholders, to work units/individuals?
Have you identified stakeholder concerns/fears and appeals
What are the specific desired behavior changes needed to support the change (what behaviors do you want more of or less of?)

## Slide 41
PARADIGMS
“If you want to create incremental change, focus on behavior. But if you want a real breakthrough, change the paradigm.”
S.R. Covey

## Slide 42
“Leadership is about change. It’s about taking people from where they are now to where they need to be. The best way to get people to venture into unknown terrain is to make it desirable by taking them there in their imagination- “FIRST.”
Noel M. Tichy, The Leadership Engine

## Slide 43: Making the End-State Actionable
End-State Description
Paradigm
Behavior
.

## Slide 45: End State Key Messages Worksheet
List Desired Behavior Changes
List Compelling Descriptive Words and Phrases
Draft End State Description/Key Messages
More of
Less of

## Slide 46
CURRENT STATE
TRANSITION STATE
FUTURE
STATE
1. Leading the Change
2. Framing the Shared Need
4. Mobilizing Commitment
Define
the
Change
Step 1
Step 2
Step 3
Leading Change Model
3. Describing the End State

## Slide 47: MOBILIZING COMMITMENT OUTCOMES
A coalition or network of committed individuals who are visibly supporting the change effort
A plan to win the support of each key stakeholder

## Slide 48
Mobilizing Commitment
Who are the key “stakeholders” who have an interest or may be affected by this change? (They may be customers – both internal and external, other functional groups, managers, employees, etc.)
2. What will likely be their response to both the need and the vision you are proposing?
3. What is the nature of the resistance you may encounter from various stakeholders? Will it be technical, political or cultural?
What support will be required from each stakeholder to reach your new “end-state” or achieve your mission?
What approaches/strategies can you employee to mobilize supporters and win over resisters?

## Slide 49: PRINCIPLES OF RESISTANCE
There is no change without resistance
Resistance doesn’t indicate something is wrong; it indicates something is happening
It is either overt or covert
The invoice – “Pay me no or pay me later”
.

## Slide 50
Resistance | Definition | Examples | Ways to Address
TECHNICAL | Aligning and structuring organization Habit and inertia Difficulty learning Sunk costs Lack of skills |  | Provide resources and training Involve in solutions
POLITICAL | Allocating power and resources Threats to old guard from new guard Relationships Power and authority imbalance or self preservation |  | Seek input and involve Sponsor team consensus and visibility
CULTURAL | Articulating the glue or cultural norms Selective perception Locked into old “mind set” Afraid of letting go |  | Create positive new paradigm
Types Of Resistance

## Slide 51: Acceptance Curve
15% INNOVATORS
35%
EARLY ADOPTERS
35%
LATE ADOPTERS
15% RESISTORS

## Slide 52: COMMITMENT ANALYSIS WORKSHEET
Identify and list key stakeholders or stakeholder groups
Rank their current commitment level
Estimate their needed commitment level for your change to succeed – i.e., how important are they to the success of this particular change
From the current and needed estimation – identify which stakeholders are most important for you to focus your efforts
Brainstorm/identify strategies to increase commitment amongst that group.
Strategies to Raise Commitment level of Key Stakeholders
Needed Commitment (Low-Med-High)
Current Commitment
(Low-Med-High)
Stakeholders

## Slide 53: Key Success Factors For Closing “Gaps”
Demonstrating one’s own commitment to change
Involving all stakeholders in change teams and processes
Asking questions – seeking input, then listening, listening and listening more
Using resource teams to shape your solutions and build a network of support
Using the “3 D’s” Prove it!
Using “need” and “vision” language to build new paradigm
“Communicating, communicating, and then communicating more”

## Slide 54
CURRENT STATE
TRANSITION STATE
FUTURE
STATE
1. Leading the Change
2. Framing the Shared Need
3. Shaping the Vision
4. Mobilizing Commitment
5. Identifying Systems and Levers for
Alignment
Define
the
Change
Step 1
Step 2
Step 3
Leading Change Model

## Slide 55
Identifying & Aligning Systems
Which “levers” – systems, structures, and processes act as barriers in blocking team success or in discouraging performance towards the change goal?
Which levers will we need to “leverage” or modify to support our change?
Which of those levers or barriers do we have influence over?
How can we influence the change or modify the systems and levers so that they will be aligned with your change
What is your “Communications Plan” for communicating through the change?

## Slide 56: ALIGNING SYSTEMS, STRUCTURES, AND LEVERS:
1. Staffing
2. Training & developing
3. Measures, rewards and recognition
4. Communication
5. Organization Structure
6. Information systems
7. Budgeting & measurement systems
8. Performance planning & review process
9. Policies and Procedures

## Slide 57
Assess the impact that organizational levers have in reinforcing or blocking your change.
High
Med
Low
Identify which levers will serve as rein forcers or barriers to your change. List them under the triangles
Indicate the degree (low, medium, high) to which that barrier can positively or negatively impact the change by writing an “X” on the Profile in the appropriate spaces
Identify which levers are within your control to change and mark a solid circle around it
Identify which levers your can influence and mark a dotted circle around it. For those you will need to identify key “owners” and define ways you can influence them to make adjustments to the system.
Identifying Levers for Alignment Worksheet

## Slide 58: STAFFING
Problem symptoms:
Best practices:
“Best” people leave; “Worst” people stay.
Key positions open too long
Great candidates turn us down.
Confusion about “what it takes” to succeed.
Too many key jobs filled from the outside.
Lack of skills to move quickly.
Lots of depth but no breadth.
Candidate sources are broad & diverse (internal and external) source of “track record” is monitored.
“Screens” include “what it takes to succeed” – both technical skills and “fit” with the business values/culture.
Multiple data sources (e.g., interview, references, past experience, tests, performance history) are gathered and weighted.
Interviewing is structured, planned, consistent, competency based, with rigorous numerical ratings taken from multiple interviewers.
Promotions are experience and performance, not seniority based.
Assignments are based on the best fit and business goals, not expediency; Developmental moves are identified and utilized.
People who are not meeting expectations are coached/developed or moved out, not “shelved” or promoted.

## Slide 59: Training & Development
Problem Symptoms:
Best practices:
“Go to training” is the standard response in coaching discussions.
Too much depth, too little breadth.
Few mentors available or qualified.
Human resources is responsible for development.
“Stars” leave; “worst” people stay.
New titles and promotions are created without real change.
People have inflated views of their performance or potential.
No time for training; training is a “perk” not an ongoing process.
Promotions usually made from within the function.
Key positions filled externally.
Using key assignments to develop high potentials
Frequent open discussion between manager and employee about career interests, expectations and prospects; with action planning.
“Fatal flaws” (e.g., incompatible values, inability to lead, inflexibility) identified for business and each job and communicated.
Mentors assigned to new hires and and promotions.
Coaching behaviors are trained, practiced and rewarded.
Trainees report on learning application after courses. Feedback provided to trainers and designers.
Customers and suppliers (internal and external) help design training.
Involve all as coaches or trainers in areas of expertise and interest; team members coach each other.
Dual career paths allow technical people to develop and be rewarded, without becoming managers.

## Slide 60: REWARDS VS. RHETORIC
Given the option of acting on the rhetoric or following the reward system, people will follow the reward system every time.

## Slide 61: RECOGNITION AND REWARD CHECKLIST
Getting a letter from my boss praising my performance.
Dong interesting and exciting work.
Receiving a good performance review.
Getting more vacation time for years of service.
Working with people who are interesting and who enjoy working with me.
Getting special attention and extra coaching time from my boss.
Being able to have access to a vehicle or lap top computer, or other such ‘benefits”.
Being listened to when I give my opinion on an important issue.
Seeing my ideas being put into action.
Being verbally praised by my boss.
Being included in a special bonus pool because of my grade level.
Successfully completing an assignment that makes a difference to the business.
Getting a promotion based on my past performance.
Learning new things.
Getting a raise based on my performance.
Receiving a special reward for doing something. ie: a trip overseas
Being praised by others for doing good work.
Getting time off for having given “extra effort”.
Directions: What motivates you and makes you feel valued? Please circle 9 of the following 18 types of rewards and recognition that you find most meaningful. Select those that are most likely to motivate you to maintain or improve your performance.

## Slide 62: SCORE SHEET
Record your answers below and total the number of items in each group.
Group A
1
3
6
10
16
18
Group B
4
7
11
13
15
17
Group C
2
5
8
9
12
14
Answer Key: The response group with the highest cumulative score indicates the primary motivator.
A = Extrinsic motivators – recognition and reward provided by one’s boss
B = Extrinsic motivators – recognition and reward provided by the organization and/or its members
C = Intrinsic motivators – recognition and reward provided by one’s own feelings/experiences with the work itself
Totals: ________ _________ _________

## Slide 63
Aligning Key Levers Worksheet
What are the high priority systems and levers that will affect your change initiative? Why must these be addressed? From whom do you need help and by when, in order for the Change Initiative to be successful?
Key Levers Affecting Your Change: | How the Lever affects the Change Initiative | What issue needs to be addressed? | By when?

## Slide 64
CURRENT STATE
TRANSITION STATE
FUTURE
STATE
1. Leading the Change
2. Framing the Shared Need
3. Shaping the Vision
4. Mobilizing Commitment
5. Identifying Systems and Levers for
Alignment
6. Communicating the
Change
Define
the
Change
Step 1
Step 2
Step 3
Leading Change Model

## Slide 65
Communicating the Change
What are the key messages that need to be communicated about the change?
To what degree do your messages need to be tailored to different stakeholder groups?
What are the best vehicles to use to communicate different change messages? What combination of written, verbal, and face-to-face communications should be used?
Who should the various change messages come from to be most impactful?
Who will be responsible for developing and implementing your “Communications Plan” through the change?

## Slide 66: COMMUNICATION DURING CHANGE
BETRAYAL
DENIAL
IDENTITY CRISIS
SEARCH FOR SOLUTIONS

## Slide 67: COMMUNICATION DURING CHANGE CHECKLIST
  Betrayal
  Keep everything out in the open
  Be honest and realistic with promises / commitments
  Be aware; reactions will be forthcoming
  Be patient
  Remain non-defensive
  Denial
  Give directions / instructions clearly and slowly
  Be specific with assignments
  Be sure you are understood
  Challenge assumptions
  Set incremental goals with short time frames
  Follow up on goals / assignments closely
  Identity Crisis
  Listen accurately
  Be supportive
  Provide opportunities for people to vent
  Recognize short-term and incremental successes
Motivate to the hilt
Keep people highly involved in the change
Tolerate mistakes
Do not tolerate equilibrium
Raise the performance bar
Continually re-recruit your people
Increase direction while clarifying communication
Be visible
Spend time one-on-one
Minimize surprises
Search for solutions
Focus on feedback, not on success or failure
Reinforce hopefulness
Continue to manage the change closely
Allow for differences in recovery time
Expect some setbacks

## Slide 68: TYPES OF COMMUNICATION
WRITTEN (least effective, but important)
+
EVENTS (most dramatic; can be either large or small)
+
ONE-ON-ONE (most effective; person must be credible)

## Slide 69
Communications Plan Worksheet
Audience(s) | Desired Outcome | Responsibility | Medium | Message | Time line

## Slide 70
CURRENT STATE
TRANSITION STATE
FUTURE
STATE
1. Leading the Change
2. Framing the Shared Need
3. Shaping the Vision
4. Mobilizing Commitment
5. Identifying Systems and Levers for
Alignment
6. Communicating the
Change
Tracking Progress
Define
the
Change
Step 1
Step 2
Step 3
Leading Change Model

## Slide 71
Tracking Progress
1. Who will want to know if your changes succeeds? (Sponsors, Boss, Stakeholders, etc.) How will they measure it- or be measured by it?
2. How will you measure success in the project? What will your “scorecard” include?
3. How will you establish a “baseline” for each key scorecard area against which you can track your progress?
4. How might measurement activity affect your project?
5. What additional benefits or opportunities may appear as “by-products” of your project activity?

## Slide 72: TRACKING PROGRESS AND OUTCOMES
1. Measure performance results as well as change activity/ process
2. Ensure Measurement Plan links back to the outputs of pervious steps
3. Develop key indicators to track different aspects of progress
  Desired end state/outcomes
  Desired behavior changes
  Concerns/fears and benefits for different stakeholders
  Required changes in polices, systems, structures
4. Establish “Base lines” early
5. Track Assumptions periodically

## Slide 73
“Whatever you measure, you will likely get.”

## Slide 74: Top 10 Measurement Mistakes
Tracking output/outcome metrics that cannot be influenced or controlled.
Gathering data that tells you what you already know.
Gathering data for it’s own sake.
Relying heavily on customer satisfaction surveys.
Executives focusing on detailed metrics.
Not linking measures to the strategic plan.
Failing to define practical correlations between key metrics.
Reporting data that is difficult to read and analyze.
Using “superstitious” process metrics.
Using measures that drive the wrong performance.

## Slide 75: 10 Tips For A Good Measurement Plan
Has clear links to strategic objectives and defines practical correlation between key indicators
Tracks process as well as results; includes measures for “T” as well as “C”
Tracks indicators at all levels - Sponsors, change agents and targets
Indicators are SMART - Simple, Measurable, Attributable, Reliable; Time-bound
Includes a well-defined plan for data analysis and its use
Maximizes the use of existing sources and systems of information gathering
Avoids information overload
Includes measures that drive individual performance balancing competitive invigoration and collaborative teamwork
Ensures clear assignment of staff, their roles and budget for tracking progress
Follows the principle of ‘optimal’ ignorance

## Slide 76: Tracking Progress Scorecard Worksheet
Strategic Objective/ Milestone | Critical Success Measures | Impact Indicators | Impact Target/ Intended Results

## Slide 77
CURRENT STATE
TRANSITION STATE
FUTURE
STATE
1. Leading the Change
2. Framing the Shared Need
3. Shaping the Vision
4. Mobilizing Commitment
5. Identifying Systems and Levers for
Alignment
6. Communicating the
Change
Tracking Progress
Define
the
Change
Develop a
Detailed
Implementation
Plan
Step 1
Step 2
Step 3
Leading Change Model

## Slide 78
Developing the Implementation Plan
What are the critical activities, deliverables, and milestones are required to successfully implement the?
Have you included both the technical activities as well as the commitment building aspects identified upon consideration of the seven framework elements?
Who is responsible to lead or complete each of the activities
In what timeframe must each activity be completed
Are change activities integrated with other ongoing activities and initiatives?

## Slide 79: Implementation Plan Worksheet
Change Management Objectives | Key Activities | When | Who/ Lead | Resources/Support Needed
1. Identify critical change roles, get agreement from change sponsor and launch the team(s) Identify key stakeholders for your change Develop a compelling Need Statement for your Change Develop a clear, behavioral end statement for you change Assess stakeholder commitment and develop strategies to address resistance Develop and implement an ongoing Change Communication Plan Develop behavior and process level indicators for your change and plan for how to measure progress. | 1. 2. 3. 1. 2. |  |  | 

## Slide 80: CHECKLIST FOR CREATING SUSTAINABLE CHANGE
Reinforce consistently – keep communications coming.
Demonstrate your commitment.
Integrate new initiatives into on-going work processes.
Sustain your attention.
Incorporate learning from past mistakes.
Accept ambiguity in the midst of change.
Expect and measure results, but focus on learning.
Redirect, let go or move on, when necessary.

## Slide 81: Your Feedback
Please take a few minutes to complete the short assessment below. Read the statements about the Leading Change Program and then select a number from 1 to 5, to indicate how much you agree or disagree with them. For the last statement, you will select a number to represent your overall rating of the program.
[1 = strongly disagree; 5 = strongly agree]
1
2
3
4
5
1.
The program was easy to understand.
2.
I have a greater appreciation for the importance of being able to effectively Lead Change at CARE’.
3.
I feel that the content of this program was relevant to my work at CARE.
4.
I learned something I did not know about Leading Change Initiatives.
5.
I have a better understanding of the critical factors to consider when planning a Change Initiative.
6.
I will refer to these materials as a reference as I work on change initiatives in the future.
7.
This is my overall rating for the program.
(Use the number 1 to represent the lowest rating and 5 the highest rating.)
Please e-mail this page to careacademy@care.org , or you may print off a copy and fax it to: (404) 577-9418 or mail to: Meg Burns, CARE Academy Program Manager, 151 Ellis Street, NE, Atlanta, GA 30303-2440.
Thank you for your participation! We encourage you to share this program, “Leading Change”, with your colleagues. If you would like to suggest additional program topics or feedback, please send an email to: careacademy@care.org.