## ActivityList (hidden)
Construction Activity | Inspection/Test Requirement | CA1 | CA2 | CA3 | PA1 | PA2 | PA3
On Site Meeting | Record of meeting to be completed | bar: CA1; PA1
Trenching | Photo's/Video of trench demonstrating correct depth, Underground Cable Installation Checklist | bar: CA1
Conduit Installation | Underground Cable installation Checklist | bar: CA1
Trench Backfilling | Evidence of use of sand and danger tape to be provided, Underground Cable Installation Checklist | bar: CA1
HV Cable Laying/Installing | Cable Laying/Pulling Record (over 200m), Underground Cable Installation Checklist | bar: CA1
LV Cable Laying/Installing | Cable Laying/Pulling Record (over 200m), Certificate of Test LV cables, Underground Cable Installation Checklist | bar: CA1 to CA2
LV Pillar installation | Low Voltage Pillar Checklist | bar: CA1
Streetlight Foundation Installation | Public Lighting Checklist | bar: CA1
Streetlight Installation | Public Lighting Checklist | bar: CA1
Package/Kiosk Substation Foundation Installation | Evidence of Earthing and Certificate of Earth Test, Package/Kiosk Substation Checklist | bar: CA1 to CA2
Package/Kiosk Substation Installation | Package/Kiosk Substation Checklist, Certificate of Test Ground Mounted Transformer | CA1: T; CA2: DP; PA1: W
Line Cleared and Poles Pegged
Poles Erected and Dressed | Distribution Pole Checklist, Certificate of Evidence Concrete/hole depth | bar: CA1
Guys Installed | Guy Checklist | bar: CA1
Overhead Transformer, Switch and MEN Installed | Certificate of Earth Test, Pole Mounted Switch Checklist, Pole Mounted Transformer Checklist | bar: CA1
Transformers and Switches installed | Pole Mounted Switch Checklist, Pole Mounted Transformer Checklist | bar: CA1
Indoor Substation Building Completed | Certificate of Earth Test, Certificate of Occupancy | bar: CA1
Indoor Substation Assets Installed | Indoor Substation Checklists | bar: CA1
Final Inspection | Project manager and Contractor carry out joint Audit and Compile Defects (All checklists and Certificate of Tests must be available) - Defects Report Developed by Project Manager | bar: CA1; PA1
Defects Rectified | Contractor notifies PM defects have been rectified | bar: PA1
Contractor Handover | Contractor Handover completed when all work and initial defects from Final inspection have been complete | bar: CA1; PA1

## Lists (hidden)
Time | Interval | YesNo
7:00 | 0:15 | Yes
7:15 |  | No
7:30
7:45
8:00
8:15
8:30
8:45
9:00
9:15
9:30
9:45
10:00
10:15
10:30
10:45
11:00
11:15
11:30
11:45
12:00
12:15
12:30
12:45
13:00
13:15
13:30
13:45
14:00
14:15
14:30
14:45
15:00
15:15
15:30
15:45
16:00
16:15
16:30
16:45
17:00

## Inspection and Test Plan
Inspection and Test Plan |  |  | "Enter Project Name" |  |  |  | Date Submitted: | 2026-07-30 |  |  |  | Plan Version: |  | Draft
Contractor: | "Enter Contractor Company" |  |  | Cont Project Manager: |  | "Enter Contractor PM" |  | Contact Number: | [5 empty] | "Enter Contractor Phone No."
Project Start: | "Enter Project Start Date" |  |  | Project End: |  | "Enter Project End Date" |  | PWC Project Manager: | [5 empty] | "Enter PWC PM"
Construction Activity |  | Notes | Start Date | End Date | Inspection/Test Requirement |  |  | Contractor |  |  | PWC PM |  |  | Appointment |  | Completed
[8 empty] | CA1 | CA2 | CA3 | PA1 | PA2 | PA3 | Date | Time
Blank |  |  |  |  | #N/A |  |  | #N/A | #N/A | #N/A | #N/A | #N/A